## Project Estimate
<COMPANY NAME> Project Estimates <DATE>
Project Estimates | Rate | Lo Hrs. | Hi Hrs. | Lo Cost Est | Hi Cost Est | Formatting | Short Rate Name | Long Rate Name | P1% | P2% | P3% | P1LOW | P1HI | P1COSTLO | P1COSTHI | P2LOW | P2HI | P2COSTLO | P2COSTHI | P3LOW | P3HI | P3COSTLO | P3COSTHI | Description
Clarity Connect License (Core Modules) | CL |  |  | 17100 | 17100 | Red | License | Clarity Connect Software License (typically $17,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 17100 | 17100 | 0 | 0 | 0 | 0 | *One-time base license for the Clarity Connect platform. Includes any connectors for the CRM/ERP/EMR that we're trying to connect to if they already exist. **Annual maintenance can be purchased for 30% of the cost of the license. This includes a small bucket of hours which can be used for tech support, training, enhancements, etc. Additional hours may be purchased at the standard rates. | Clarity Connect Licensing & Standard Configuration
- 1st Application integrated | CL |  |  | 0 | 0 | Red | License | Clarity Connect Software License (typically $17,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *<FIRST APPLICATION>
- 2nd Application integrated | CL |  |  | 0 | 0 | Red | License | Clarity Connect Software License (typically $17,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *<SECOND APPLICATION>
Basic Connect Client configuration package | i |  |  | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *Clarity will prepare a package / documents that will allow the client to review and make choices on the installation and configuration of the integration. This will include the the fields mappings worksheet (if the client is going to do the mappings), instructions and information about where the integration platform will be hosted.
Basic Connect installation (Dev) | i |  |  | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - Clarity will install (in the dev environment), the basic OOTB Connect installation. The client will be responsible for providing credentials/access to a test account or environment for the applications being connected.
Basic Connect configuration | i |  |  | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - There are numerous features that are configurable based on where the solution will be installed, what queue and database will be used, etc. This line item will be used to set up those basic features.
Basic Connect QA (validation of features, etc.) | i |  |  | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - For the OOTB features, Clarity will provide QA/quality control to test the implementation once your products have been installed and content posted. The client will be responsible for final QA and sign off for pushing to production.
Basic Push to Production | i |  |  | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - Once the site has passed UAT, Clarity will push the install to production. **This may be variable if the client wants a more complex hosting environment set up (i.e. behind their DMZ, custom queue or database, etc.). If the client chooses an outside hosting provider (themselves, AWS, Azure, etc.), then the client is responsible for any hosting fees.
Integration customizations | I | -11 | -11 | -1650 | -1650 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | -11 | -11 | -1650 | -1650 | 0 | 0 | 0 | 0 | *The client is provided a total of 20 hours for integration customizations. In order to be able to provide custom development, there will be a need for a Project Manager to be assigned, as well as some meeting time to discuss the customizations, and finally some QA time to validate any customizations. With those all built in, this leaves you 13 hours for actual custom development. You may use this for customizing the integration workflows, helping with the field mappings, adding in custom entities, etc. Any time above the 13 hours used will be billed at the standard rates. Removed from the total project hours | Connectors and Customizations
Discovery - Technical Analysis | i | 22 | 26 | 3300 | 3900 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) | 100% |  |  | 22 | 26 | 3300 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for the Clarity BA Team to conduct Discovery Sessions to document Business Logic and Client-Specific Requirements
Discovery - Documentation | i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for the Clarity BA Team to create and FSD (Functional Specification Document) that details all client-specific customizations (User Stories, Notes, and Related Documents)
Discovery - Re-Estimations | i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for Clarity's BA Team to conduct a formal Re-Estimations Meeting to task out and estimate all features in the FSD.
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i |  | 0 | 0 | 0 | Orange | Integration | Integration Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Discovery | BA | 2 | 3 | 300 | 450 | Dark Yellow | Business Analyst | Business Analysts normally required with projects needing BE development) |  | 100% |  | 0 | 0 | 0 | 0 | 2 | 3 | 300 | 450 | 0 | 0 | 0 | 0 | *Unit and pre-launch use case testing | PM, QA, & Meetings
QA, Bug Fix, User Story testing | QA | 2 | 2 | 300 | 300 | Dark Yellow | Quality Assurance | Quality Assurance (typically 15%, 10% for FE-only projects) |  | 100% |  | 0 | 0 | 0 | 0 | 2 | 2 | 300 | 300 | 0 | 0 | 0 | 0
Meetings | MTG | 1 | 1 | 150 | 150 | Blue | Meetings | 5-10% based on project size, client (person, team, committee) |  | 100% |  | 0 | 0 | 0 | 0 | 1 | 1 | 150 | 150 | 0 | 0 | 0 | 0 | *Depends on clients' needs (more meetings, more people = more time)
Project Management | PM | 4 | 5 | 500 | 625 | Dark Green | Project Management | Project Management (20% < $75k, 15% > $75k) |  | 100% |  | 0 | 0 | 0 | 0 | 4 | 5 | 500 | 625 | 0 | 0 | 0 | 0 | *Clarity Project Management, Invoicing, Sprint planning, Gantt, etc.
Projected Estimate |  | 20 | 26 | 20000 | 20875
Preferred (Pre-paid) Hourly Block Rates & Licensing Costs |  | Lo Rate | Hi Rate
Front-end Development rate | F | 125 | 125 |  | Phase I & II hours | Phase I & II $ |  |  | Total Cost
Back-end, Middle-end Development rate | B/M | 150 | 150 |  | 20 | 0 | 0 | 0 | 20000
Quality Assurance, Discovery, Business Analyst rate | QA/DD/BA | 150 | 150 |  | 20 | 0 | 0 | 0 | 20000
Integration Development rate | I | 150 | 150
SEO / marketing work rate | SE/MK | 175 | 175 |  | Phase III hours | Phase I & II $ |  |  | Total Cost
Project Management | PM | 125 | 125 |  | 0 | 0 | 0 | 0 | 0
Clarity eCommerce software license | EL | 20000 | 20000 |  | 0 | 0 | 0 | 0 | 0
Clarity Connect software license | CL | 17000 | 17000
*NOTE: Standard (Post pay) rate @ + $25/hr.
Note on Z9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes Developer QA of initial installation

## Summary
Project Hours Breakdown by Group / Phase
Row Labels | Low Hrs | Hi Hrs | Low Rate | Hi Rate | PI Lo Hr | PI Hi Hr | Phase 1 Lo | Phase 1 Hi | P2 Lo Hr | P2 Hi Hr | Phase 2 Lo | Phase 2 HI | P3 Lo Hr | P3 Hi Hr | Phase 3 Lo | Phase 3 Hi
Integration | 13 | 13 | 1950 | 1950 | 0 | 0 | 0 | 0 | 13 | 13 | 1950 | 1950 | 0 | 0 | 0 | 0
License |  | 0 | 17100 | 17100 | 0 | 0 | 0 | 0 | 0 | 0 | 17100 | 17100 | 0 | 0 | 0 | 0
Meetings | 1 | 1 | 150 | 150 | 0 | 0 | 0 | 0 | 1 | 1 | 150 | 150 | 0 | 0 | 0 | 0
Project Management | 4 | 4 | 500 | 500 | 0 | 0 | 0 | 0 | 4 | 4 | 500 | 500 | 0 | 0 | 0 | 0
Quality Assurance | 2 | 2 | 300 | 300 | 0 | 0 | 0 | 0 | 2 | 2 | 300 | 300 | 0 | 0 | 0 | 0
Grand Total | 20 | 20 | 20000 | 20000 | 0 | 0 | 0 | 0 | 20 | 20 | 20000 | 20000 | 0 | 0 | 0 | 0

## Draw Schedule
Based on the current cost estimate for your project we are currently recommending 1 weeks of UAT testing by your team. |  |  |  |  | 0.4
0.4
1
|  | Project-based Payments |  |  | 1
Cost Per Month
| Month | Month Name | Total
| 6 | June | 10000 | 1
| 7 | July | 10000 | 1.878
| Grand Total |  | 20000 | 2.655

## MonthLookup (hidden)
MonthNum | MonthName
1 | January
2 | February
3 | March
4 | April
5 | May
6 | June
7 | July
8 | August
9 | September
10 | October
11 | November
12 | December
13 | January
14 | February
15 | March
16 | April
17 | May
18 | June
19 | July
20 | August
21 | September
22 | October
23 | November
24 | December

## Draw Schedule Config
| Starting Month | 5 | Column1 | Column2 |  |  |  | 5 | 9 | 1
|  | Weeks | Cost | Cost Per Week | Week | Month | Month Name | Ignore1 | Ignore2 | Ignore3 | P1Cost | P2Cost | P3Cost | Cost
| Phase 1 | 4 | 0 | 0 | Week 1 | 5 | May | 4 | 9 | 1 | 0 |  |  | 0
| Phase 2 | 8 | 20000 | 2500 | Week 2 | 5 | May | 3 | 9 | 1 | 0 | 0 | 0 | 0
| Phase 3 |  | 0 | 0 | Week 3 | 5 | May | 2 | 9 | 1 | 0 | 0 | 0 | 0
[5 empty] | Week 4 | 5 | May | 1 | 9 | 1 | 0 | 0 | 0 | 0
[5 empty] | Week 5 | 6 | June | 0 | 8 | 1 | 0 | 2500 | 0 | 2500
[5 empty] | Week 6 | 6 | June | 0 | 7 | 1 | 0 | 2500 | 0 | 2500
| Column1 | Column2 | Column3 | Column4 | Week 7 | 6 | June | 0 | 6 | 1 | 0 | 2500 | 0 | 2500
| Variance Months | % |  |  | Week 8 | 6 | June | 0 | 5 | 1 | 0 | 2500 | 0 | 2500
| 1 |  |  | 20000 | Week 9 | 7 | July | 0 | 4 | 1 | 0 | 2500 | 0 | 2500
1 | Variance | % | Variance Amount |  | Week 10 | 7 | July | 0 | 3 | 1 | 0 | 2500 | 0 | 2500
2 | 1 | 0 | 0 |  | Week 11 | 7 | July | 0 | 2 | 1 | 0 | 2500 | 0 | 2500
3 | 0 | 0 | 0 |  | Week 12 | 7 | July | 0 | 1 | 1 | 0 | 2500 | 0 | 2500
4 | -1 | 0 | 0 |  | Week 13 | 8 | August | 0 | 0 | 0 | 0 | 0 | 0 | 0
| -2 | 0 | 0 |  | Week 14 | 8 | August | 0 | -1 | -1 | 0 | 0 | 0 | 0
[5 empty] | Week 15 | 8 | August | 0 | -2 | -2 | 0 | 0 | 0 | 0
[5 empty] | Week 16 | 8 | August | 0 | -3 | -3 | 0 | 0 | 0 | 0
[5 empty] | Week 17 | 9 | September | 0 | -4 | -4 | 0 | 0 | 0 | 0
[5 empty] | Week 18 | 9 | September | 0 | -5 | -5 | 0 | 0 | 0 | 0
[5 empty] | Week 19 | 9 | September | 0 | -6 | -6 | 0 | 0 | 0 | 0
[5 empty] | Week 20 | 9 | September | 0 | -7 | -7 | 0 | 0 | 0 | 0
[5 empty] | Week 21 | 10 | October | 0 | -8 | -8 | 0 | 0 | 0 | 0
[5 empty] | Week 22 | 10 | October | 0 | -9 | -9 | 0 | 0 | 0 | 0
[5 empty] | Week 23 | 10 | October | 0 | -10 | -10 | 0 | 0 | 0 | 0
[5 empty] | Week 24 | 10 | October | 0 | -11 | -11 | 0 | 0 | 0 | 0
[5 empty] | Week 25 | 11 | November | 0 | -12 | -12 | 0 | 0 | 0 | 0
[5 empty] | Week 26 | 11 | November | 0 | -13 | -13 | 0 | 0 | 0 | 0
[5 empty] | Week 27 | 11 | November | 0 | -14 | -14 | 0 | 0 | 0 | 0
[5 empty] | Week 28 | 11 | November | 0 | -15 | -15 | 0 | 0 | 0 | 0
[5 empty] | Week 29 | 12 | December | 0 | -16 | -16 | 0 | 0 | 0 | 0
[5 empty] | Week 30 | 12 | December | 0 | -17 | -17 | 0 | 0 | 0 | 0
[5 empty] | Week 31 | 12 | December | 0 | -18 | -18 | 0 | 0 | 0 | 0
[5 empty] | Week 32 | 12 | December | 0 | -19 | -19 | 0 | 0 | 0 | 0
[5 empty] | Week 33 | 13 | January | 0 | -20 | -20 | 0 | 0 | 0 | 0
[5 empty] | Week 34 | 13 | January | 0 | -21 | -21 | 0 | 0 | 0 | 0
[5 empty] | Week 35 | 13 | January | 0 | -22 | -22 | 0 | 0 | 0 | 0
[5 empty] | Week 36 | 13 | January | 0 | -23 | -23 | 0 | 0 | 0 | 0
[5 empty] | Week 37 | 14 | February | 0 | -24 | -24 | 0 | 0 | 0 | 0
[5 empty] | Week 38 | 14 | February | 0 | -25 | -25 | 0 | 0 | 0 | 0
[5 empty] | Week 39 | 14 | February | 0 | -26 | -26 | 0 | 0 | 0 | 0
[5 empty] | Week 40 | 14 | February | 0 | -27 | -27 | 0 | 0 | 0 | 0
[5 empty] | Week 41 | 15 | March | 0 | -28 | -28 | 0 | 0 | 0 | 0
[5 empty] | Week 42 | 15 | March | 0 | -29 | -29 | 0 | 0 | 0 | 0
[5 empty] | Week 43 | 15 | March | 0 | -30 | -30 | 0 | 0 | 0 | 0
[5 empty] | Week 44 | 15 | March | 0 | -31 | -31 | 0 | 0 | 0 | 0
[5 empty] | Week 45 | 16 | April | 0 | -32 | -32 | 0 | 0 | 0 | 0
[5 empty] | Week 46 | 16 | April | 0 | -33 | -33 | 0 | 0 | 0 | 0
[5 empty] | Week 47 | 16 | April | 0 | -34 | -34 | 0 | 0 | 0 | 0
[5 empty] | Week 48 | 16 | April | 0 | -35 | -35 | 0 | 0 | 0 | 0
[5 empty] | Week 49 | 17 | May | 0 | -36 | -36 | 0 | 0 | 0 | 0
[5 empty] | Week 50 | 17 | May | 0 | -37 | -37 | 0 | 0 | 0 | 0
[5 empty] | Week 51 | 17 | May | 0 | -38 | -38 | 0 | 0 | 0 | 0
[5 empty] | Week 52 | 17 | May | 0 | -39 | -39 | 0 | 0 | 0 | 0
[5 empty] | Week 53 | 18 | June | 0 | -40 | -40 | 0 | 0 | 0 | 0
[5 empty] | Week 54 | 18 | June | 0 | -41 | -41 | 0 | 0 | 0 | 0
[5 empty] | Week 55 | 18 | June | 0 | -42 | -42 | 0 | 0 | 0 | 0
[5 empty] | Week 56 | 18 | June | 0 | -43 | -43 | 0 | 0 | 0 | 0
[5 empty] | Week 57 | 19 | July | 0 | -44 | -44 | 0 | 0 | 0 | 0
[5 empty] | Week 58 | 19 | July | 0 | -45 | -45 | 0 | 0 | 0 | 0
[5 empty] | Week 59 | 19 | July | 0 | -46 | -46 | 0 | 0 | 0 | 0
[5 empty] | Week 60 | 19 | July | 0 | -47 | -47 | 0 | 0 | 0 | 0
[5 empty] | Week 61 | 20 | August | 0 | -48 | -48 | 0 | 0 | 0 | 0
[5 empty] | Week 62 | 20 | August | 0 | -49 | -49 | 0 | 0 | 0 | 0
[5 empty] | Week 63 | 20 | August | 0 | -50 | -50 | 0 | 0 | 0 | 0
[5 empty] | Week 64 | 20 | August | 0 | -51 | -51 | 0 | 0 | 0 | 0
[5 empty] | Week 65 | 21 | September | 0 | -52 | -52 | 0 | 0 | 0 | 0
[5 empty] | Week 66 | 21 | September | 0 | -53 | -53 | 0 | 0 | 0 | 0
[5 empty] | Week 67 | 21 | September | 0 | -54 | -54 | 0 | 0 | 0 | 0
[5 empty] | Week 68 | 21 | September | 0 | -55 | -55 | 0 | 0 | 0 | 0
[5 empty] | Week 69 | 22 | October | 0 | -56 | -56 | 0 | 0 | 0 | 0
[5 empty] | Week 70 | 22 | October | 0 | -57 | -57 | 0 | 0 | 0 | 0
[5 empty] | Week 71 | 22 | October | 0 | -58 | -58 | 0 | 0 | 0 | 0
[5 empty] | Week 72 | 22 | October | 0 | -59 | -59 | 0 | 0 | 0 | 0
[5 empty] | Week 73 | 23 | November | 0 | -60 | -60 | 0 | 0 | 0 | 0
[5 empty] | Week 74 | 23 | November | 0 | -61 | -61 | 0 | 0 | 0 | 0
[5 empty] | Week 75 | 23 | November | 0 | -62 | -62 | 0 | 0 | 0 | 0
[5 empty] | Week 76 | 23 | November | 0 | -63 | -63 | 0 | 0 | 0 | 0
[5 empty] | Week 77 | 24 | December | 0 | -64 | -64 | 0 | 0 | 0 | 0
[5 empty] | Week 78 | 24 | December | 0 | -65 | -65 | 0 | 0 | 0 | 0
[5 empty] | Week 79 | 24 | December | 0 | -66 | -66 | 0 | 0 | 0 | 0
[5 empty] | Week 80 | 24 | December | 0 | -67 | -67 | 0 | 0 | 0 | 0
[5 empty] | Variance 1 | 90 | Variance - 1 | 0 | -68 | -68 | 0 | 0 | 0 | 0
[5 empty] | Variance 2 | 91 | Variance - 2 | 0 | -69 | -69 | 0 | 0 | 0 | 0
[5 empty] | Variance 3 | 92 | Variance - 3 | 0 | -70 | -70 | 0 | 0 | 0 | 0
[5 empty] | Variance 4 | 93 | Variance - 4 | 0 | -71 | -71 | 0 | 0 | 0 | 0

## Configuration Table
Project Estimates Legend
Code | Preferred Rate | Lo-Hi Range | % Of Dev | Short Name | Type of Product / Service | Color
F | 125 | 15% |  | Front End | Front End Hourly Rate ($150/hr. for post-pay) | Blue
B | 150 | 15% |  | Back End | Back End Hourly Rate ($175/hr. for post-pay) | Yellow
M | 150 | 15% |  | Middle End | Middle End Hourly Rate ($175/hr. for post-pay) | Green
I | 150 | 15% |  | Integration | Integration Hourly Rate ($175/hr. for post-pay) | Orange
MK | 175 | 15% |  | Marketing | Marketing Hourly Rate ($200/hr. for post-pay) | Grey
SE | 175 | 15% |  | SEO | SEO Hourly Rate ($200/hr. for post-pay) | Grey
EL | 20000 | 0% |  | License | Clarity eCommerce Software License (typically $20,000) | Red
CL | 17100 | 0% |  | License | Clarity Connect Software License (typically $17,000) | Red
BA | 150 | 15% | 15% | Business Analyst | Business Analysts normally required with projects needing BE development) | Dark Yellow
PM | 125 | 0% | 20% | Project Management | Project Management (20% < $75k, 15% > $75k) | Dark Green
QA | 150 | 0% | 15% | Quality Assurance | Quality Assurance (typically 15%, 10% for FE-only projects) | Dark Yellow
MTG | 150 | 0% | 5% | Meetings | 5-10% based on project size, client (person, team, committee) | Blue
CMARK | 2500 | 0% |  | License | Marketing Machine Learning Engine | Red
CSTORE | 5000 | 0% |  | License | Multi-store Module | Red
CLANG | 5000 | 0% |  | License | Multi-Currency / Multi-lingual | Red
DD | 125 | 15% |  | Discovery | Project Discovery and Documentation | Yellow