## Project Estimate
<COMPANY NAME> Project Estimates
Project Estimates | Rate | Lo Hrs. | Hi Hrs. | Lo Cost Est | Hi Cost Est | Formatting | Short Rate Name | Long Rate Name | P1% | P2% | P3% | P1LOW | P1HI | P1COSTLO | P1COSTHI | P2LOW | P2HI | P2COSTLO | P2COSTHI | P3LOW | P3HI | P3COSTLO | P3COSTHI | Description
Clarity eCommerce License (Core Modules) | EL |  |  | 19300 | 19300 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 19300 | 19300 | 0 | 0 | 0 | 0 | *One-time base license for the Clarity eCommerce platform. Includes all "base modules" below needed for the estimated project (unless otherwise specified - i.e. multi-store, multi-lingual, etc.). **Annual maintenance can be purchased for 30% of the cost of the license. This includes a small bucket of hours which can be used for tech support, training, enhancements, etc. Additional hours may be purchased at the standard rates. | eCommerce Licensing
- Carts (checkout, mini, micro carts install) | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Address Book, Wallet Modules | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Seller / Product Ratings, Comments & Approvals | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Basic promotions / discounts / pricing rules Modules | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Guest checkout, Quick Order Modules | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Predictive Autofill for search | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- User / Admin Dashboard Modules | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Lists - Shopping, Wish, Favorites, Notify me | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Catalog - Categories, Products, Attributes, SEO, Inventory | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Reporting Engine | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- Clarity API Module | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing & Machine Learning Engine Modules | CMARK |  |  | 0 | 0 | Red | License | Marketing Machine Learning Engine |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *Custom logic module used to record user behavior (i.e. visitor looks @ category multiple times, serve up coupon for that category, etc.).
Multi-store Module | CSTORE |  |  | 0 | 0 | Red | License | Multi-store Module |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *Either separate branded stores, or multi-seller marketplaces (eBay, etc.)
Multi-Currency / Multi-lingual Modules | CLANG |  |  | 0 | 0 | Red | License | Multi-Currency / Multi-lingual |  |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *Either multi-lingual or currency for international (includes menu, navigation translations). Does NOT include client products, content.
Basic CEF Client configuration package | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *Clarity will prepare a package / documents that will allow the client to review and make choices on the installation and configuration of the site (i.e. which merchant account are you using, which shipping carrier, are we calculating sales tax, etc.). Once the client has provided the responses, Clarity will custom configure the installation and stand it up, ready for the client to start adding site content and storefront products. | Included eCommerce Configuration
Basic CEF installation | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - Clarity will install (in the dev environment), the basic OOTB CEF installation, and create credentials for you to add content/products.
Basic CEF configuration | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - There are numerous features that may or may not be wanted for your installation (B2B features turned off for a B2C site, etc.), or B2B features turned on (invoicing, warehousing, etc.).
Basic CEF QA (validation of features, etc.) | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - For the OOTB features, Clarity will provide QA/quality control to test the implementation once your products have been installed and content posted. The client will be responsible for final QA and sign off for pushing to production.
Basic Push to Production | EL |  |  | 0 | 0 | Red | License | Clarity eCommerce Software License (typically $20,000) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | *included - Once the site has passed UAT, Clarity will push the site to production. **This may be variable if the client wants a more complex hosting environment set up (i.e. load balancing, CDN, etc.). If the client chooses an outside hosting provider (themselves, AWS, Azure, etc.), then the client is responsible for any hosting fees.
Site/Storefront customizations | B | 28 | 28 | 4200 | 4200 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 28 | 28 | 4200 | 4200 | 0 | 0 | 0 | 0 | *The client is provided a total of 40 hours for customizations. In order to be able to provide custom development, there will be a need for a Project Manager to be assigned, as well as some meeting time to discuss the customizations, and finally some QA time to validate any customizations. With those all built in, this leaves you 28 hours for actual custom development. You may use this for website styling, custom modules (blog, forms, faqs, etc.), or customizations on the storefront (i.e. invoicing, reporting, help with prepping your product data for bulk import, etc.). Any time above the 28 hours used will be billed at the standard rates. Deducted from total project hours
Discovery - Technical Analysis | BA |  | 0 | 0 | 0 | Dark Yellow | Business Analyst | Business Analysts normally required with projects needing BE development) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for the Clarity BA Team to conduct Discovery Sessions to document Business Logic and Client-Specific Requirements | eCommerce Customizations
Discovery - Requirements Documentation | BA |  | 0 | 0 | 0 | Dark Yellow | Business Analyst | Business Analysts normally required with projects needing BE development) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for the Clarity BA Team to create and FSD (Functional Specification Document) that details all client-specific customizations (Features Description, User Stories, Notes, and Related Documents)
Discovery - Re-Estimations | BA |  | 0 | 0 | 0 | Dark Yellow | Business Analyst | Business Analysts normally required with projects needing BE development) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for Clarity's BA Team to conduct a formal Re-Estimations Meeting to task out and estimate all features in the FSD.
Designs - Wireframes | F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for Clarity's Design Team to create wireframes for any Custom Features not already in CEF
Designs - Mockups | F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) | 100% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Time for Clarity's Design Team to apply Client-Specific Theme (Colors, Fonts, Logo, Imagery, Content) to the Wireframes for New Features and the OOB CEF Skins/Templates
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checkout - Shipping Provider Configuration | B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checkout - Tax Provider Configuration | B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checkout - Payment Provider Configuration | B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Checkout - Order Confirmation Email Template Modifications | B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| F |  | 0 | 0 | 0 | Blue | Front End | Front End Hourly Rate ($150/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B |  | 0 | 0 | 0 | Yellow | Back End | Back End Hourly Rate ($175/hr. for post-pay) |  | 100% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QA, Bug Fix, User Story testing | QA | 5 | 5 | 625 | 625 | Dark Yellow | Quality Assurance | Quality Assurance (typically 15%, 10% for FE-only projects) |  | 100% |  | 0 | 0 | 0 | 0 | 5 | 5 | 625 | 625 | 0 | 0 | 0 | 0 | *Unit and pre-launch use case testing | PM, QA, & Meetings
Meetings | MTG | 1 | 1 | 125 | 125 | Blue | Meetings | 5-10% based on project size, client (person, team, committee) | 30% | 70% |  | 0.3 | 0.3 | 37.5 | 37.5 | 0.7 | 0.7 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | *Depends on clients' needs (more meetings, more people = more time)
Project Management | PM | 6 | 6 | 750 | 750 | Dark Green | Project Management | Project Management (20% < $75k, 15% > $75k) | 30% | 70% |  | 1.8 | 1.8 | 225 | 225 | 4.2 | 4.2 | 525 | 525 | 0 | 0 | 0 | 0 | *Clarity Project Management, Invoicing, Sprint planning, Gantt, etc.
Projected Estimate |  | 40 | 40 | 25000 | 25000
Preferred (Pre-paid) Hourly Block Rates & Licensing Costs |  | Lo Rate | Hi Rate
Front-end Development rate | F | 125 | 125 |  | Phase I & II hours | Phase I & II $ |  |  | Total Cost
Back-end, Middle-end Development rate | B/M | 150 | 150 |  | 60 | 0 | 0 | 0 | 44995
Quality Assurance, Discovery, Business Analyst rate | QA/DD/BA | 150 | 150 |  | 60 | 0 | 0 | 0 | 44995
Integration Development rate | I | 150 | 150
SEO / marketing work rate | SE/MK | 175 | 175 |  | Phase III hours | Phase I & II $ |  |  | Total Cost
Project Management | PM | 125 | 125 |  | 0 | 0 | 0 | 0 | 0
Clarity eCommerce software license | EL | 20000 | 20000 |  | 0 | 0 | 0 | 0 | 0
Clarity Connect software license | CL | 17000 | 17000
*NOTE: Standard (Post pay) rate @ + $25/hr.

## Summary
Project Hours Breakdown by Group / Phase
Row Labels | Low Hrs | Hi Hrs | Low Rate | Hi Rate | PI Lo Hr | PI Hi Hr | Phase 1 Lo | Phase 1 Hi | P2 Lo Hr | P2 Hi Hr | Phase 2 Lo | Phase 2 HI | P3 Lo Hr | P3 Hi Hr | Phase 3 Lo | Phase 3 Hi
Back End | 13 | 13 | 1950 | 1950 | 0 | 0 | 0 | 0 | 13 | 13 | 1950 | 1950 | 0 | 0 | 0 | 0
Front End | 28 | 28 | 3500 | 3500 | 0 | 0 | 0 | 0 | 28 | 28 | 3500 | 3500 | 0 | 0 | 0 | 0
License | 0 | 0 | 37170 | 37170 | 0 | 0 | 0 | 0 | 0 | 0 | 37170 | 37170 | 0 | 0 | 0 | 0
Meetings | 2 | 2 | 250 | 250 | 0 | 0 | 0 | 0 | 2 | 2 | 250 | 250 | 0 | 0 | 0 | 0
Project Management | 10 | 10 | 1250 | 1250 | 0 | 0 | 0 | 0 | 10 | 10 | 1250 | 1250 | 0 | 0 | 0 | 0
Quality Assurance | 7 | 7 | 875 | 875 | 0 | 0 | 0 | 0 | 7 | 7 | 875 | 875 | 0 | 0 | 0 | 0
Grand Total | 60 | 60 | 44995 | 44995 | 0 | 0 | 0 | 0 | 60 | 60 | 44995 | 44995 | 0 | 0 | 0 | 0

## Draw Schedule
Based on the current cost estimate for your project we are currently recommending 1 weeks of UAT testing by your team. |  |  |  |  | 0.9
0.9
1
|  | Project-based Payments |  |  | 1
Cost Per Month
| Month | Month Name | Total
| 9 | September | 15000 | 1
| 10 | October | 15000 | 1.878
| 11 | November | 15000 | 2.655
| Grand Total |  | 45000

## MonthLookup (hidden)
MonthNum | MonthName
1 | January
2 | February
3 | March
4 | April
5 | May
6 | June
7 | July
8 | August
9 | September
10 | October
11 | November
12 | December
13 | January
14 | February
15 | March
16 | April
17 | May
18 | June
19 | July
20 | August
21 | September
22 | October
23 | November
24 | December

## Draw Schedule Config
| Starting Month | 9 | Column1 | Column2 |  |  |  | 3 | 13 | 1
|  | Weeks | Cost | Cost Per Week | Week | Month | Month Name | Ignore1 | Ignore2 | Ignore3 | P1Cost | P2Cost | P3Cost | Cost
| Phase 1 | 2 | 0 | 0 | Week 1 | 9 | September | 2 | 13 | 1 | 0 | 0 | 0 | 0
| Phase 2 | 12 | 44995 | 3750 | Week 2 | 9 | September | 1 | 13 | 1 | 0 | 0 | 0 | 0
| Phase 3 |  | 0 | 0 | Week 3 | 9 | September | 0 | 12 | 1 | 0 | 3750 | 0 | 3750
[5 empty] | Week 4 | 9 | September | 0 | 11 | 1 | 0 | 3750 | 0 | 3750
[5 empty] | Week 5 | 10 | October | 0 | 10 | 1 | 0 | 3750 | 0 | 3750
[5 empty] | Week 6 | 10 | October | 0 | 9 | 1 | 0 | 3750 | 0 | 3750
| Column1 | Column2 | Column3 | Column4 | Week 7 | 10 | October | 0 | 8 | 1 | 0 | 3750 | 0 | 3750
| Variance Months | % |  |  | Week 8 | 10 | October | 0 | 7 | 1 | 0 | 3750 | 0 | 3750
| 1 |  |  | 44995 | Week 9 | 11 | November | 0 | 6 | 1 | 0 | 3750 | 0 | 3750
1 | Variance | % | Variance Amount |  | Week 10 | 11 | November | 0 | 5 | 1 | 0 | 3750 | 0 | 3750
2 | 1 | 0 | 0 |  | Week 11 | 11 | November | 0 | 4 | 1 | 0 | 3750 | 0 | 3750
3 | 0 | 0 | 0 |  | Week 12 | 11 | November | 0 | 3 | 1 | 0 | 3750 | 0 | 3750
4 | -1 | 0 | 0 |  | Week 13 | 12 | December | 0 | 2 | 1 | 0 | 3750 | 0 | 3750
| -2 | 0 | 0 |  | Week 14 | 12 | December | 0 | 1 | 1 | 0 | 3750 | 0 | 3750
[5 empty] | Week 15 | 12 | December | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Week 16 | 12 | December | 0 | -1 | -1 | 0 | 0 | 0 | 0
[5 empty] | Week 17 | 13 | January | 0 | -2 | -2 | 0 | 0 | 0 | 0
[5 empty] | Week 18 | 13 | January | 0 | -3 | -3 | 0 | 0 | 0 | 0
[5 empty] | Week 19 | 13 | January | 0 | -4 | -4 | 0 | 0 | 0 | 0
[5 empty] | Week 20 | 13 | January | 0 | -5 | -5 | 0 | 0 | 0 | 0
[5 empty] | Week 21 | 14 | February | 0 | -6 | -6 | 0 | 0 | 0 | 0
[5 empty] | Week 22 | 14 | February | 0 | -7 | -7 | 0 | 0 | 0 | 0
[5 empty] | Week 23 | 14 | February | 0 | -8 | -8 | 0 | 0 | 0 | 0
[5 empty] | Week 24 | 14 | February | 0 | -9 | -9 | 0 | 0 | 0 | 0
[5 empty] | Week 25 | 15 | March | 0 | -10 | -10 | 0 | 0 | 0 | 0
[5 empty] | Week 26 | 15 | March | 0 | -11 | -11 | 0 | 0 | 0 | 0
[5 empty] | Week 27 | 15 | March | 0 | -12 | -12 | 0 | 0 | 0 | 0
[5 empty] | Week 28 | 15 | March | 0 | -13 | -13 | 0 | 0 | 0 | 0
[5 empty] | Week 29 | 16 | April | 0 | -14 | -14 | 0 | 0 | 0 | 0
[5 empty] | Week 30 | 16 | April | 0 | -15 | -15 | 0 | 0 | 0 | 0
[5 empty] | Week 31 | 16 | April | 0 | -16 | -16 | 0 | 0 | 0 | 0
[5 empty] | Week 32 | 16 | April | 0 | -17 | -17 | 0 | 0 | 0 | 0
[5 empty] | Week 33 | 17 | May | 0 | -18 | -18 | 0 | 0 | 0 | 0
[5 empty] | Week 34 | 17 | May | 0 | -19 | -19 | 0 | 0 | 0 | 0
[5 empty] | Week 35 | 17 | May | 0 | -20 | -20 | 0 | 0 | 0 | 0
[5 empty] | Week 36 | 17 | May | 0 | -21 | -21 | 0 | 0 | 0 | 0
[5 empty] | Week 37 | 18 | June | 0 | -22 | -22 | 0 | 0 | 0 | 0
[5 empty] | Week 38 | 18 | June | 0 | -23 | -23 | 0 | 0 | 0 | 0
[5 empty] | Week 39 | 18 | June | 0 | -24 | -24 | 0 | 0 | 0 | 0
[5 empty] | Week 40 | 18 | June | 0 | -25 | -25 | 0 | 0 | 0 | 0
[5 empty] | Week 41 | 19 | July | 0 | -26 | -26 | 0 | 0 | 0 | 0
[5 empty] | Week 42 | 19 | July | 0 | -27 | -27 | 0 | 0 | 0 | 0
[5 empty] | Week 43 | 19 | July | 0 | -28 | -28 | 0 | 0 | 0 | 0
[5 empty] | Week 44 | 19 | July | 0 | -29 | -29 | 0 | 0 | 0 | 0
[5 empty] | Week 45 | 20 | August | 0 | -30 | -30 | 0 | 0 | 0 | 0
[5 empty] | Week 46 | 20 | August | 0 | -31 | -31 | 0 | 0 | 0 | 0
[5 empty] | Week 47 | 20 | August | 0 | -32 | -32 | 0 | 0 | 0 | 0
[5 empty] | Week 48 | 20 | August | 0 | -33 | -33 | 0 | 0 | 0 | 0
[5 empty] | Week 49 | 21 | September | 0 | -34 | -34 | 0 | 0 | 0 | 0
[5 empty] | Week 50 | 21 | September | 0 | -35 | -35 | 0 | 0 | 0 | 0
[5 empty] | Week 51 | 21 | September | 0 | -36 | -36 | 0 | 0 | 0 | 0
[5 empty] | Week 52 | 21 | September | 0 | -37 | -37 | 0 | 0 | 0 | 0
[5 empty] | Week 53 | 22 | October | 0 | -38 | -38 | 0 | 0 | 0 | 0
[5 empty] | Week 54 | 22 | October | 0 | -39 | -39 | 0 | 0 | 0 | 0
[5 empty] | Week 55 | 22 | October | 0 | -40 | -40 | 0 | 0 | 0 | 0
[5 empty] | Week 56 | 22 | October | 0 | -41 | -41 | 0 | 0 | 0 | 0
[5 empty] | Week 57 | 23 | November | 0 | -42 | -42 | 0 | 0 | 0 | 0
[5 empty] | Week 58 | 23 | November | 0 | -43 | -43 | 0 | 0 | 0 | 0
[5 empty] | Week 59 | 23 | November | 0 | -44 | -44 | 0 | 0 | 0 | 0
[5 empty] | Week 60 | 23 | November | 0 | -45 | -45 | 0 | 0 | 0 | 0
[5 empty] | Week 61 | 24 | December | 0 | -46 | -46 | 0 | 0 | 0 | 0
[5 empty] | Week 62 | 24 | December | 0 | -47 | -47 | 0 | 0 | 0 | 0
[5 empty] | Week 63 | 24 | December | 0 | -48 | -48 | 0 | 0 | 0 | 0
[5 empty] | Week 64 | 24 | December | 0 | -49 | -49 | 0 | 0 | 0 | 0
[5 empty] | Week 65 | 25 | #N/A | 0 | -50 | -50 | 0 | 0 | 0 | 0
[5 empty] | Week 66 | 25 | #N/A | 0 | -51 | -51 | 0 | 0 | 0 | 0
[5 empty] | Week 67 | 25 | #N/A | 0 | -52 | -52 | 0 | 0 | 0 | 0
[5 empty] | Week 68 | 25 | #N/A | 0 | -53 | -53 | 0 | 0 | 0 | 0
[5 empty] | Week 69 | 26 | #N/A | 0 | -54 | -54 | 0 | 0 | 0 | 0
[5 empty] | Week 70 | 26 | #N/A | 0 | -55 | -55 | 0 | 0 | 0 | 0
[5 empty] | Week 71 | 26 | #N/A | 0 | -56 | -56 | 0 | 0 | 0 | 0
[5 empty] | Week 72 | 26 | #N/A | 0 | -57 | -57 | 0 | 0 | 0 | 0
[5 empty] | Week 73 | 27 | #N/A | 0 | -58 | -58 | 0 | 0 | 0 | 0
[5 empty] | Week 74 | 27 | #N/A | 0 | -59 | -59 | 0 | 0 | 0 | 0
[5 empty] | Week 75 | 27 | #N/A | 0 | -60 | -60 | 0 | 0 | 0 | 0
[5 empty] | Week 76 | 27 | #N/A | 0 | -61 | -61 | 0 | 0 | 0 | 0
[5 empty] | Week 77 | 28 | #N/A | 0 | -62 | -62 | 0 | 0 | 0 | 0
[5 empty] | Week 78 | 28 | #N/A | 0 | -63 | -63 | 0 | 0 | 0 | 0
[5 empty] | Week 79 | 28 | #N/A | 0 | -64 | -64 | 0 | 0 | 0 | 0
[5 empty] | Week 80 | 28 | #N/A | 0 | -65 | -65 | 0 | 0 | 0 | 0
[5 empty] | Variance 1 | 90 | Variance - 1 | 0 | -66 | -66 | 0 | 0 | 0 | 0
[5 empty] | Variance 2 | 91 | Variance - 2 | 0 | -67 | -67 | 0 | 0 | 0 | 0
[5 empty] | Variance 3 | 92 | Variance - 3 | 0 | -68 | -68 | 0 | 0 | 0 | 0
[5 empty] | Variance 4 | 93 | Variance - 4 | 0 | -69 | -69 | 0 | 0 | 0 | 0

## Configuration Table
Project Estimates Legend
Code | Preferred Rate | Lo-Hi Range | % Of Dev | Short Name | Type of Product / Service | Color
F | 125 | 15% |  | Front End | Front End Hourly Rate ($150/hr. for post-pay) | Blue
B | 150 | 15% |  | Back End | Back End Hourly Rate ($175/hr. for post-pay) | Yellow
M | 150 | 15% |  | Middle End | Middle End Hourly Rate ($175/hr. for post-pay) | Green
I | 150 | 15% |  | Integration | Integration Hourly Rate ($175/hr. for post-pay) | Orange
MK | 175 | 15% |  | Marketing | Marketing Hourly Rate ($200/hr. for post-pay) | Grey
SE | 175 | 15% |  | SEO | SEO Hourly Rate ($200/hr. for post-pay) | Grey
EL | 19300 | 0% |  | License | Clarity eCommerce Software License (typically $20,000) | Red
CL | 17000 | 0% |  | License | Clarity Connect Software License (typically $17,000) | Red
BA | 150 | 15% |  | Business Analyst | Business Analysts normally required with projects needing BE development) | Dark Yellow
PM | 125 | 0% | 15% | Project Management | Project Management (20% < $75k, 15% > $75k) | Dark Green
QA | 125 | 0% | 15% | Quality Assurance | Quality Assurance (typically 15%, 10% for FE-only projects) | Dark Yellow
MTG | 125 | 0% | 3% | Meetings | 5-10% based on project size, client (person, team, committee) | Blue
CMARK | 2500 | 0% |  | License | Marketing Machine Learning Engine | Red
CSTORE | 5000 | 0% |  | License | Multi-store Module | Red
CLANG | 5000 | 0% |  | License | Multi-Currency / Multi-lingual | Red
DD | 125 | 15% |  | Discovery | Project Discovery and Documentation | Yellow