## 12.14-1.4
ID | Work Item Type | User Story | Task | State | Tags | Iteration Path | Original Estimate | Remaining Work | Completed Work
100611 | Bug | [DERM] Billing address on checkout form is missing second line for apt suite |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04
100614 | Task |  | [DERM] Update check out form for billing addy to have line 2 | Closed | DERM | CEF-Product\2022\Sprint-11.30-12.13 | 2 |  | 3
100617 | Task | [DERM] Ensure stage is a one to one match with prod |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 2 |  | 3.5
100843 | User Story | [DERM] Paypal payment provider documenation review and integration |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 10 |  | 10
100844 | Task |  | [DERM] PayPal Payment provider documenation reivew and intial set up | Closed | DERM | CEF-Product\2022\Sprint-11.30-12.13 | 4 |  | 3.5
101360 | Task |  | [DERM] PayPal Integrated config and set up | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 10 |  | 11.25
101365 | Task | [DERM] Ensure that all consumer products have 0 stock/ Ensure that add to cart buttons replaced with amazon/ walmart links |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 2 |  | 2
102209 | Task | [DERM] Email templates and triggers |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 3 |  | 3
102698 | Task | [DERM] Troubleshoot check out issues |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 2 |  | 3
102893 | Task | [DERM] Update Header on homepage |  | Closed | DERM | CEF-Product\2022\Sprint-12.14-01.04 | 0.5 |  | 0.5
| PM | [5 empty] | 8 |  | 14.25
| QA | [5 empty] | 5 |  | 10
[6 empty] | Hours estimated vs worked | 48.5 |  | 64
Rate 150 per hrs
[6 empty] | Hrs balance at start and end of sprint | 100 |  | 36

## 1.5-1.17
ID | Work Item Type | Title 1 | Title 2 | State | Tags | Iteration Path | Original Estimate | Remaining Work | Completed Work | Current Hrs balance
100612 | Bug | [DERM] Check out redirects to wrong intake form for ED meds and always displays Toenail Fungus intake page |  | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 |  |  |  | 21.75
100613 | Task |  | [DERM] Investigate redirect for Intake form and ensure it goes to the correct splash page | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 2 | 2 | 0
102890 | User Story | [DERM] Update Header on homepage |  | In Development | DERM | CEF-Product\2023\Sprint-01.05-01.17
103101 | Task |  | [DERM] Update Header on Home page | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 5 | 5 | 0
103108 | Task |  | [DERM] Update Header on homepage | New | DERM | CEF-Product | 1 | 3 | 0
102929 | User Story | [DERM] Add buttons linking to Walmart and Amazon to the product template for consumer products |  | New | DERM | CEF-Product\2023\Sprint-01.05-01.17
103058 | Task |  | [DERM] Add buttons linking to Walmart and Amazon to the product template for consumer products | Active | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 1 | 1 | 0
103042 | User Story | [DERM] Push to production |  | New | DERM | CEF-Product\2023\Sprint-01.05-01.17
102926 | Task |  | [DERM] SEO Implementation | New | DERM | CEF-Product |  |  | 0
103043 | Task |  | [DERM] Ensure that Redis cache is cleared for each push to production | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 1 | 1 | 0
103044 | Task |  | [DERM] Staging environment checkout | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 1 | 1 | 0
103109 | Task |  | [DERM] UAT bucket | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 5 | 5 | 0
103110 | Task |  | [DERM] UAT bucket | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 4 | 4 | 0
103111 | Task |  | [DERM] Client remediation and UAT bucket | New | DERM | CEF-Product\2023\Sprint-01.05-01.17 | 5 | 5 | 0
|  |  | zoho support |  |  |  | 4
|  |  | PM |  |  |  | 6
[6 empty] | Sprint Hrs | 35 | Rate 150 | 5250
[6 empty] | Hrs needed to keep balance at 100 hrs positive | 40 | Rate 150 | 6000
[6 empty] | Sprint invoice total |  |  | 11250